## All
PRD
Stakeholder(s) | Feature category | Feature Request | Use case/ Description | Severity | Priority | Near/ Mid term | Status | Owner | Request date | Requestor | Target Resolution date | Actual Resolution Date | Notes
Buyers | UX | Consistent & validated size chart that is easy to find | Update all product pages with new size chart showing UK & US sizing |  | P0 | Near | Done | Glory Babalola
Buyers | Trust/ Support | Request specific measurements needed for made to order | A field entry for each key measurements required for a vendor to be able to fulfil the order |  | P0 | Near | Done | Glory Babalola
Buyers | Core | Updated home page | Clean & easy to follow home page sectioned into one featured page, shops ( Work from office, elevated essentials, Special occasions, Vacay bae/Snow birds, Casual chic, Bold Prints) and best sellers. Filter by body type (Busty, Tall, Petite, Plus Size) |  | P0 | Mid | Done | Lere Solomon Awosupin
Buyers | Logistics | Fast and reliable checkout and shipping tracking | Make every products on site, 2Kg and usethat to inform a DHL shipping options |  | P0 | Near | Done | Lere Solomon Awosupin |  |  |  |  | Need to implement DHL component
Buyers | Trust/ Support | Social proof (reviews, ratings, user photos) | Need to review the automations |  | P0 | Near
Buyers | UX | Personalized recommendations | A user should be able to see items similar to what they're interested in or have added to cart in the past. "because you viewed this" , "wishlist" section |  | P1 | Mid |  | Lere Solomon Awosupin
Buyers |  | Remove out of stock items | We don't want any product to show out of stock on the homepage |  | P0 | Near |  | Lere Solomon Awosupin
Buyers | UX | Simple browsing, intuitive filtering (style, region, category) |  |  | P0 | Mid
Buyers | Logistics | Live order tracking and delivery updates |  |  | P0 | Mid
Buyers | UX | Accesibility features (read screen, live chat, AI shopping assisstant) |  |  | P0 | Mid
Buyers | UX | Push notifications for deals |  |  | P0 | Mid
Buyers | UX | Style quiz incorporation | Uses data from style quizzes(digital stylist) and browsing patterns to surface relevant looks, complete outfits & optimize size guide. |  | P1 | Mid
Buyers | Finance | Localization (USD/CAD currencies, cross‑border delivery estimates) |  |  | P0 | Long
Buyers | UX | Curated/Styled cart | A user should see a curated list of items that go well together with the option to select & add all to cart at once e.g. the pants that completes the set for a top |  | P2 | Long
Buyers | AI/ Data | Rich storytelling (designer backgrounds, origin stories) |  |  | P0
Platform Core & Operations | Core | eCommerce Website fast page load speed and performance optimization |  |  | P0 | Mid
Platform Core & Operations | Core | SEO optimization to improve global visibility on search engines |  |  | P0 | Near
Platform Core & Operations | Handling/Fulfilment | Handling details improvement. No import charges for all local warehouse items and no extra charges upon delivery | include two options: 1. "ships within 24-48 hrs" for RTW 2. "Requires processing" for Made-to-order (learn more) |  | P0 | Near | [6 empty] | Discuss in HLT
Platform Core & Operations | Handling/Fulfilment | Shipping from CA, US or from outside of Africa options |  |  | P0 | Near | Done
Platform Core & Operations | Logistics | Shipping options 3-4 | Include all 4 options with different pricing options: 1. 3PL last mile cheap 2. In US/CA (bulk 3PL) 3. DHL - speedy shipping |  | P0 | Mid | Done | Lere Solomon Awosupin
Platform Core & Operations | UX | Label individual brands accurately on the platform including dedicated brand pages |  |  | P0 | Near | Done
Platform Core & Operations | Handling/Fulfilment | Notification to sellers and progress updates automatic tracking | Automatic notifcation to sellers when new order comes , excluding customer PIIs. this should also link to a workflow on haanta where the brands can update workflow for order fulfilment |  | P0 | Long | [6 empty] | Review in automations
Platform Core & Operations | Core | Scalable cloud hosting to handle order surges during periods of high demands |  |  | P0 | Mid
Platform Core & Operations | Finance | Financial data security and detection of suspicious transactions |  |  | P0 | Mid
Platform Core & Operations | Core | Implement workflow where vendors can add, modify and update their own products from their systems. this system should trigger a manual review from an Haanta employee befiore it goes live |  |  | P0 | Mid
Platform Core & Operations | UX | Product detail page to include variants, size charts and emphasize variation e.g. this brand runs long |  |  | P0 | Mid
Platform Core & Operations | AI/ Data | Data science & AI driven trendspotting - this will inform the products that is displayed on the homepage, informing sales behavior and conversions |  |  | P1 | Mid
Platform Core & Operations | Core | Customer supprt ticketing to monitor latency, downtimes, and potential issues from buyers or sellers in a unified dashboard |  |  | P1 | Mid
Platform Core & Operations | AI/ Data | Recommender system: based on specific user behavior to inform products that would appeal to customer e.g. a luxury customer to be shown similar products, and a price sensitive customer be shown products based on their behavious |  |  | P1 | Long
Platform Core & Operations | UX | Gamification: Similar to Temu & Shein, we would like to gamify buying behavior similar to the ezisiting behavior from users in this segment - e.g. when there’s a new drop, brand communicate urgency and linmited stock, gamifying this experience would be essential |  |  | P2 | Long
Platform Core & Operations | AI/ Data | Future: Scrapping and testing propducts not listed on Haanta to inform new lines for the customers. |  |  | P2 | Long
Sellers | AI/ Data | Automated stock alerts (low stock, bestsellers) |  |  | P1 | Long
Sellers | UX | Easy onboarding and listing tools (product photos, variant setup, storytelling templates) | Self-serve store front for sellers to upload & manage inventory |  | P0 | Mid | [6 empty] | Near
Sellers | Logistics | Clear payout and logistics workflows |  |  | P1 | Mid
Sellers | UX | Vendor training/ onboarding videos |  |  | P3 | Mid
Sellers | Logistics | Integration & API/ plugins for partner website: this designed to help reroute checkout through the Haanta platform when sales is from North America | should a wide variety of API integration with most eCommerce APIs e.g. social, logistics, after sales support, etc. |  | P1 | Long
Sellers | AI/ Data | Vendor insights (sales analytics, customer behavior) |  |  | P2 | Long | [6 empty] | Long
Sellers | Trust/ Support | Marketing support (promo integration, featured collections) |  |  | P2 | Long
Sellers | Logistics | Inventory, shipping, and payment dashboards |  |  | P1 | [7 empty] | Mid
Sellers | AI/ Data | Product performance comparisons | Leverage AI to skim websites |  | P2
Sellers | Logistics | Cross border sales support |  |  | P2
Platform Core & Operations | UX | Shipping Origin | Pre-order products currently display “Ships from Houston,” as their shipping origin which is inaccurate. | S3 | P2 | Near | In progress | Julius | 2026-09-06 |  | 2026-09-06
Platform Core & Operations | UX | Product Display Inconsistencies | There is inconsistency in product card formatting across the website. A consistent product display structure should be adopted sitewide. | S3 | P2 | Near | Done | Julius
Platform Core & Operations | UX | Brands Page Issues | “Pre-Order” and “Shop Now,” as well as "Shop Now" Pop-Out styling buttons have poor contrast and blend into the background. | S3 | P2 | Near | Done | Julius
Platform Core & Operations | UX | Discover Page | Text overlays on images should have improved contrast/readability for better visibility. | S3 | P1 | Near | Done | Julius |  |  | 2026-05-06
Platform Core & Operations | UX | Filter Issues | General Filter Problems: When filters are applied, some information gets cut off at the bottom. Filter by Color should use text labels instead of only colored circles. Please remove unnecessary filters such as: Filter by Dimension, Filter by Length (cm). Additionally, there are currently multiple “Filter by Size” filters (approximately six), retain only one consistent size filter relevant to shoppers | S3 | P2 | Near |  | Julius |  |  |  |  | Filter is a wix default, and what can only be changed is it categories to filter.
Buyers | Core | Checkout & Delivery Issues | There is a checkout error involving delivery profiles when some products are added to cart together. Users may be unable to complete checkout due to delivery profile conflicts especially from Alaska, Oregon, and Hawaii | S0 | P0 | Near | Done | Julius |  |  | 2026-05-06
Platform Core & Operations | Core | Free Shipping Issue | Free shipping does not appear to be functioning correctly, as some orders above 250 are still being charged shipping fees. | S0 | P0 | Near | Done | Julius |  |  | 2026-05-06
Platform Core & Operations | UX | Product Information Issues | Some size fields are incorrectly displaying colors instead. | S2 | P1 | Near | Done | Julius |  |  | 2026-05-06
Platform Core & Operations | UX | Ships From US Page | The “Ships From US” page can be removed from mobile navigation/site structure. | S3 | P2 | Near | Done | Julius |  |  | 2026-05-06
Platform Core & Operations | UX | Popup Issues | “Be in the List” popup appears too frequently on mobile. | S2 | P2 | Near |  | Julius |  |  |  |  | This is also a Wix default issue
Platform Core & Operations | Core | Checkout Page UI | Checkout page text/layout feels too large and oversized on mobile. | S2 | P2 | Near |  | Julius |  |  |  |  | This is a Wix default that cannot be adjusted even with VeloCode, I would have to reduce the site Master Style size for this to reduce and it would affect the whole site
Platform Core & Operations | UX | Homepage Layout | The mobile homepage currently feels too busy and visually overcrowded. It could be a bit more simplified with a cleaner visual hierarchy | S2 | P1 | Near | Done | Julius |  |  | 2026-05-06
Platform Core & Operations | UX | New Overlay Mega Menu |  | S2 | P2 |  | Done | Julius | 2026-07-31 | Lere | 2026-08-07 | 2026-08-06
Platform Core & Operations | Core | Randomization of Product Display |  | S1 | P1 |  | Done | Julius | 2026-07-27 | Lere | 2026-07-31 | 2026-08-04
Platform Core & Operations | UX | Shop By Brands |  | S2 | P2 |  |  | Julius |  | Faith
Platform Core & Operations | Trust/ Support | Setting Up Meta and TikTok Shop with Dinma) |  | S2 | P1 |  | In progress | Julius | 2026-08-03 | Lere | 2026-08-07
Platform Core & Operations | Trust/ Support | Analytics of website traffic on pages and Key incidents. |  | S1 | P1 |  | In progress | Julius | 2026-08-03 | Lere | 2026-08-09
Platform Core & Operations | UX | Return Policy Page |  | S1 | P1 |  | Done | Julius | 2026-08-03 | Faith | 2026-08-07 | 2026-08-05
Buyers | UX | Product Color selector | Some prouduts with multiple color options like the "Spiky Thalia" and "Ada Skirt Set" do not have a color selector. Different colors are pictured but there is only an "add to cart button" so customers don't have the option to select which color they want to buy | S1 | P1 |  | Done | Julius | 2026-08-06 | Sade | 2026-08-09 | 2026-08-08
Platform Core & Operations | UX | Product Color selector | Right now, when a product has multiple color options, all the different options are displayed. Could we make it so that is the default load, but when customers click on a color option, only the product images that is of that color is displayed? | S3 | P2 |  |  | Julius | 2026-08-06 | Sade |  |  | This would not work. Most of the products do not have the available color options image. Most have just 2 images and may have more than that 2 color variant option
Buyers | UX | Review Color options and images | I haven't done an extensive search but I came across the Sorelle Women's Runched Bodice Peplum Top from Meliria and the color options available to chose from are Green and Brown, but the product images only show a black and white option. Is there a way for us to quickly cross check our product listing pictures and color options to make sure they're aligned? | S1 | P1 |  |  | Julius | 2026-08-06 | Sade |  |  | This further explains my point. Products image available on the vendor website can be green and black but the client can have the products in 4 more different variants withiut the images of those. It is the vendor/seller that have control over images not us.
Platform Core & Operations | UX | "You might like this" and a "More from this brand" section on a product page. | Right now, product pages only include the prodcuct so the user's shopping experience "ends" as soon as they click a product. Adding a section underneath the product pages will nudge customers to continue browsing | S3 | P2 |  |  | Julius | 2026-08-06 | Sade | 2026-08-09
Platform Core & Operations | UX | Remove "Load More" button on product page | Having to click the "Load More" button once the customer gets to the end of loaded content disrupts the buyer's experience. Can we make it so once the customer gets to the end of the pre-loaded products, the site automocatilly reloads the next set of images instead of the customers having to click a "load more" button. | S3 | P2 |  | Done | Julius | 2026-08-06 | Sade | 2026-08-08 | 2026-08-08
Platform Core & Operations | UX | Size guide accuracy | Products are sized as Size/UK#/US# but the size guide only includes size which can be confusing if we have multiple size options for Medium. Can we update the size guide so it also includes the UK#/US#? Also, we're using the same size guide for different brands. Is sizing consistent across all the brands? Is there a need to create custom size guides for brands? | S2 | P2 |  |  | Julius | 2026-08-06 | Sade
Platform Core & Operations | UX | Mobile site: View all button is displaced on the home page under the "Browse More" section | Move it to the bottom of the section | S1 | P1 |  |  | Julius | 2026-08-06 | Sade | 2026-08-07
Platform Core & Operations | UX | Mobile site: Add margins to the left and right side of the page | Text is cut off from on the left side of page so adding margins could help. Or any other solution you have to fixing. | S1 | P1 |  | Done | Julius | 2026-08-06 | Sade | 2026-08-08 | 2026-08-07
Platform Core & Operations | UX | Mobile site: Banner - Only the "Shop Mora Collection" banner appears on the mobile site and the banner is not clickable |  | S2 | P2 |  | Done | Julius | 2026-08-06 | Sade | 2026-08-09
Platform Core & Operations | UX | Mobile site: Banner - Text on banner image is cut off | The banner is getting cut off on the mobile version so any long text that spans the length of the banner gets cut off and any text not in the center of the banner does not get shown | S2 | P2 |  | Done | Julius | 2026-08-06 | Sade | 2026-08-07 | 2026-08-07
Platform Core & Operations | UX | Duplicate filters | There are 3 filters for Bamigugu in the search and you get different results depending on whuch filter you select. | S3 | P3 |  |  | Julius | 2026-08-06 | Sade | 2026-08-08
Buyers | Trust/ Support | Duplicate Product | We have two Tor Aso Oke Caps. Same design, different prices. https://www.haanta.com/product-page/tor-aso-oke-cap-1 ($44) https://www.haanta.com/product-page/tor-aso-oke-cap ($51) | S1 | P2 |  | Done | Julius | 2026-08-06 | Sade | 2026-08-07
Buyers | Trust/ Support | Duplicate Product | The Asooke Cap - Fila and the Ebuka Aso Oke Cap have the same exact product picture https://www.haanta.com/product-page/asooke-cap-fila https://www.haanta.com/product-page/ebuka-aso-oke-cap | S2 | P2 |  | Done | Julius | 2026-08-06 | Sade | 2026-08-07 | 2026-08-07
Buyers | Trust/ Support | Duplicate Product | There are two versions of the Line Art Jalabiya Cap and Set https://www.haanta.com/product-page/line-art-jalabiya-and-cap-set https://www.haanta.com/product-page/line-art-white-jalabiya-and-cap-set | S2 | P2 |  | Done | Julius | 2026-08-06 | Sade | 2026-08-07 | 2026-08-08
Platform Core & Operations | AI/ Data | Add Tiktok Pixel code to site | It will allows us to track web traffic from Tiktok ads and also allows us to create targeted ads on Tiktok to people who have enagaged with our site | S2 | P2 |  |  | Julius | 2026-08-08 | Sade
Platform Core & Operations | AI/ Data | Add Meta Pixel code to site | Same functionality as tiktok pixel but with Facebook/Instagram | S2 | P2 |  |  | Julius | 2026-08-08 | Sade
Platform Core & Operations | AI/ Data | Add Meta Conversions code to site | Helps with ad marketing | S2 | P2 |  |  | Julius | 2026-08-08 | Sade
Platform Core & Operations | AI/ Data | Add Google Tag code to site | Same functionality as tiktok pixel but with Google/Google Ads/Youtube | S2 | P2 |  |  | Julius | 2026-08-08 | Sade
Platform Core & Operations | UX | Shop Mora banner link is a 404 Error code |  | S1 | P1 |  | Done | Julius | 2026-08-10 | Sade | 8/11/0206 | 2026-08-11
Platform Core & Operations | UX | Ready to ship from US banner link is a 404 Error code |  | S1 | P1 |  | Done | Julius | 2026-08-10 | Sade | 2026-08-11 | 2026-08-11
Platform Core & Operations | UX | Modern Men's tailoring banner link is a 404 Error code |  | S1 | P1 |  | Done | Julius | 2026-08-10 | Sade | 2026-08-11 | 2026-08-11
Buyers | Logistics | Ada skirt set is one the options that show up when we click "Shipped from the US" but on the product page it says "This item is expected to ship from Nigeria within 15 - 20 business days." Can we confirm where this material ships from and categorize it properly? | Product link: https://www.haanta.com/product-page/ada-skirt-set | S3 | P3 |  |  | Julius | 2026-08-10 | Sade
Buyers | Trust/ Support | Can we add fabric/material details? | Helps customers understand what they are buying and adds to our credibility | S4 | P3 |  |  | Julius | 2026-08-10 | Sade
Platform Core & Operations | Logistics | Logistics Shipping Correction and Expedited New integration |  | S0 | P0 |  | Done | Julius | 2026-08-10 | Lere | 2026-08-11 | 2026-08-14
Platform Core & Operations | Logistics | Add 5000 naira pick up fee to the 38,500 shipping fee | Total shipping fee for standard delivery will be 43,500 naira |  | P0 |  |  | Julius | 2026-07-09 | Halimat
Sellers | AI/ Data | Website Scraping | Shop Mora |  |  |  | Done | Julius |  |  | 2026-04-07
Sellers | AI/ Data | Website Scraping | Shop Nandra |  |  |  |  | Julius |  |  | 2026-04-07
Sellers | AI/ Data | Website Scraping | Bamigugu |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Lola Signatures |  |  |  | Done | Julius
Sellers | AI/ Data | Website Scraping | Tadah |  |  |  | Done | Julius |  |  | 2026-07-07
Sellers | AI/ Data | Website Scraping | Kola Kuddus |  |  |  |  | Julius |  |  |  |  | Security Issue on the website
Sellers | AI/ Data | Website Scraping | SHEISBUJINE |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Asiko |  |  |  |  | Julius |  |  | 8//7/2026
Sellers | AI/ Data | Website Scraping | Melira |  |  |  |  | Julius |  |  |  |  | Security Issue on the website
Sellers | AI/ Data | Website Scraping | Tisora |  |  |  | Done | Julius
Sellers | AI/ Data | Website Scraping | Amarelis |  |  |  | Done | Julius |  |  |  |  | Security Issue on the website
Sellers | AI/ Data | Website Scraping | Oyiza |  |  |  | In progress | Julius |  |  | 2026-02-07
Sellers | AI/ Data | Website Scraping | Maple Street |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Temade |  |  |  | Done | Julius |  |  | 2026-02-07
Sellers | AI/ Data | Website Scraping | AvrilbyWK |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Tan and Sunset |  |  |  | Done | Julius
Sellers | AI/ Data | Website Scraping | Austine Mali |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Goldstitche Handmade |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Gozi Fego |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Simona |  |  |  | Done | Julius
Sellers | AI/ Data | Website Scraping | Soso Lagos |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Liz & Co |  |  |  | Done | Julius
Sellers | AI/ Data | Website Scraping | Atuche Woman |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Folm |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Doye Brand |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Ulaku Finds |  |  |  |  | Julius
Sellers | AI/ Data | Website Scraping | Trax Apparel |  |  |  | Done | Julius
Sellers | AI/ Data | Website Scraping | Aadun & Co |  |  |  | Done | Julius

## Buyers
PRD
Stakeholder(s) | Feature category | Feature Request | Use case/ Description | Priority | Near/ Mid term
Buyers | UX | Simple browsing, intuitive filtering (style, region, category) |  | P0
Buyers | Finance | Localization (USD/CAD currencies, cross‑border delivery estimates) |  | P0
Buyers | AI/ Data | Rich storytelling (designer backgrounds, origin stories) |  | P0
Buyers | Logistics | Fast and reliable checkout and shipping tracking |  | P0
Buyers | Finance | Multiple payment options (cards, in-site wallets) |  | P0
Buyers | Logistics | Live order tracking and delivery updates |  | P0
Buyers | Trust/ Support | Social proof (reviews, ratings, user photos) |  | P0
Buyers | UX | Accesibility features (read screen, live chat, AI shopping assisstant) |  | P0
Buyers | UX | Push notifications for deals |  | P0
Buyers | UX | Fast fashion options ("wishlist", "frequently bought together", "recommended for you") |  | P0
Buyers | UX | Intuitive size chart |  | P0

## Platform Core & Operations
PRD
Stakeholder(s) | Feature category | Feature Request | Use case/ Description | Priority
Platform Core & Operations | AI/ Data | Data science & AI driven trendspotting - this will inform the products that is displayed on the homepage, informing sales behavior and conversions |  | P1
Platform Core & Operations | AI/ Data | Recommender system: based on specific user behavior to inform products that would appeal to customer e.g. a luxury customer to be shown similar products, and a price sensitive customer be shown products based on their behavious |  | P1
Platform Core & Operations | UX | Gamification: Similar to Temu & Shein, we would like to gamify buying behavior similar to the ezisiting behavior from users in this segment - e.g. when there’s a new drop, brand communicate urgency and linmited stock, gamifying this experience would be essential |  | p2
Platform Core & Operations | AI/ Data | Future: Scrapping and testing propducts not listed on Haanta to inform new lines for the customers. |  | P2
Platform Core & Operations | Core | eCommerce Website fast page load speed and performance optimization |  | P0
Platform Core & Operations | Core | Scalable cloud hosting to handle order surges during periods of high demands |  | P0
Platform Core & Operations | Core | SEO optimization to improve global visibility on search engines |  | P0
Platform Core & Operations | Finance | Financial data security and detection of suspicious transactions |  | P0
Platform Core & Operations | Core | Customer supprt ticketing to monitor latency, downtimes, and potential issues from buyers or sellers in a unified dashboard |  | P1
Platform Core & Operations | Handling/Fulfilment | Handling details improvement | include two options: 1. "ships within 24-48 hrs" for RTW 2. "Requires processing" for Made-to-order | P0
Platform Core & Operations | Logistics | Shipping options 3-4 | Include all 4 options with different pricing options: 1. 3PL last mile cheap 2. In US/CA (bulk 3PL) 3. DHL - speedy shipping | P0
Platform Core & Operations | UX | Label individual brands accurately on the platform including dedicated brand pages |  | P0
Platform Core & Operations | Core | Implement workflow where vendors can add, modify and update their own products from their systems. this system should trigger a manual review from an Haanta employee befiore it goes live |  | P0
Platform Core & Operations | UX | Product detail page to include variants, size charts and emphasize variation e.g. this brand runs long |  | P0
Platform Core & Operations | Handling/Fulfilment | Notification to sellers and progress updates automatic tracking | Automatic notifcation to sellers when new order comes , excluding customer PIIs. this should also link to a workflow on haanta where the brands can update workflow for order fulfilment | P0

## Homepage
Shop heading | Picture | Vendor | Option 2 | Vendor
Special Occasions | Nitemi Dress, | Anike Ologe | Mela | Oyiza
Elevated Essentials | Zina Shirt | GoziFego
Casual Chic | Bubble set | Liz & Co
Work From Office | Dayo Piece | Anike Ologe
Bold Prints | Fiibii | Fiibii Studio
Vacay Bae | Bubblegum Dress | Melira

## Holiday Shop
Vendor | Photo
Tadah | Soso 2 piece
Anike Ologe | Anike Special
Anike Ologe | Mma Dress
Anike Ologe | Binye